BULE HORA UNIVERSITY TEACHING HOSPITALS

CHANGE MANAGEMENT & GO-LIVE STRATEGY

Digital Hospital Management System Implementation

# 1. Change Management Strategy

## 1.1 Overview

The transition from manual to digital systems represents significant organizational change. This strategy outlines a structured approach to manage change, minimize disruption, and maximize adoption rates across all departments.

## 1.2 Stakeholder Engagement

## 1.2.1 Executive Leadership

- Monthly steering committee meetings

- Visibility into project milestones and KPIs

- Executive sponsorship and message of support

## 1.2.2 Department Heads & Clinical Leadership

- Bi-weekly department updates

- Early access to system for testing and feedback

- Role as departmental champions post-go-live

- Customization of workflows to departmental needs

## 1.2.3 Staff Members

- Transparent communication about timelines and benefits

- Regular training sessions and hands-on practice

- Feedback mechanisms and suggestion programs

- Recognition programs for early adopters

## 1.3 Communication Plan

| Audience | Communication Type | Frequency | Channel |
| --- | --- | --- | --- |
| All Staff | Project updates, benefits, timeline | Weekly | Email, Posters |
| Departments | Workflow changes, impact on processes | Bi-weekly | Meetings |
| Leadership | Progress, risks, resource needs | Monthly | Steering Comm |

# 2. Comprehensive Training Program

## 2.1 Training Curriculum Overview

All staff will receive role-specific training with multiple delivery methods including instructor-led sessions, online modules, hands-on labs, and quick-reference guides. Training will occur in phases before go-live.

## 2.2 Training Phases

## 2.2.1 Phase 1: Super User Training (Months 9-10)

- Select 2-3 super users per department

- Intensive 5-day training program

- Deep-dive into all system features

- Train-the-trainer certification

- Prepare training materials and FAQs

## 2.2.2 Phase 2: General Staff Training (Months 10-11)

- Role-specific training sessions (4 hours)

- Hands-on labs with test data

- Scenario-based practice

- Knowledge assessments and certification

## 2.2.3 Phase 3: Just-in-Time Training (Week of GO-Live)

- Quick refresher sessions

- Q&A sessions with IT support

- Distribution of quick-reference cards

## 2.3 Role-Specific Training Modules

## Physicians (Doctors)

- EMR navigation and documentation

- Order entry (medications, labs, imaging)

- Viewing patient history and results

- Drug interaction checking

## Nurses

- Patient assessment and vital signs entry

- Medication administration verification

- Patient monitoring documentation

- Admission/discharge workflows

## Receptionists

- Patient registration and check-in

- Appointment scheduling

- Insurance verification

- Queue management

## Pharmacists

- Prescription processing

- Inventory management

- Drug interaction verification

- Expiry tracking and reordering

## Laboratory Technicians

- Test requisition receipt

- Sample tracking

- Result entry and validation

- Quality assurance

# 3. GO-LIVE Plan & Checklist

## 3.1 GO-LIVE Timeline

| Date | Activity | Owner |
| --- | --- | --- |
| Day -7 | Final system testing & UAT | QA Team |
| Day -3 | Data migration from legacy system | Database Team |
| Day -1 | Final validation & cutover prep | Operations Team |
| Day 0 (GO-LIVE) | System cutover - legacy to new system | IT Operations |
| Day 0-7 | 24/7 support desk operations | Support Team |
| Week 2 | Stabilization period - monitor for issues | All teams |
| Week 3 | Lessons learned & optimization | Project Team |

## 3.2 Pre-GO-LIVE Checklist

### Technical Readiness

- ☐ All servers and databases configured and tested

- ☐ Network connectivity and security verified

- ☐ Backup and disaster recovery systems tested

- ☐ Data migration testing completed successfully

- ☐ Interface integrations tested

- ☐ Performance testing under load completed

- ☐ Security scan and penetration testing passed

### User Readiness

- ☐ 100% of users completed required training

- ☐ Super users certified as trainers

- ☐ Quick reference guides distributed

- ☐ Help desk staff trained and ready

- ☐ Test accounts created for all users

### Operational Readiness

- ☐ Vendor support plan confirmed

- ☐ Incident management procedures defined

- ☐ Fallback procedures documented

- ☐ Communication channels established

- ☐ 24/7 support desk established

- ☐ Executive leadership briefed on plan

# 4. Success Metrics & KPIs

## 4.1 System Performance Metrics

- System uptime: ≥ 99.5%

- Average response time: < 2 seconds

- Database performance: < 100ms latency

- Page load time: < 3 seconds

## 4.2 User Adoption Metrics

- Training completion rate: > 95%

- Active users at Day 30: > 90%

- User satisfaction score: > 4.0/5.0

- Help desk ticket resolution time: < 24 hours (P3), < 4 hours (P1)

## 4.3 Business Process Metrics

- Average patient registration time: reduced by 50%

- Lab result turnaround: reduced by 40%

- Appointment scheduling efficiency: +60%

- Data entry errors: reduced by 75%

- Patient wait times: reduced by 30%

## 4.4 Financial Metrics

- Billing accuracy: > 99%

- Days to payment reduction: < 10 days

- Medicine wastage reduction: 35%

- Administrative cost savings: 25% annually

## 4.5 Quality & Safety Metrics

- Medical error reduction: > 40%

- Drug interaction alerts: 95% detected

- Data integrity audits: 100% compliance

- HIPAA/compliance violations: zero

# 5. Post-GO-LIVE Support & Stabilization

## 5.1 Support Structure

- 24/7 Help Desk: Phone, Email, Chat support

- Tier 1 Support: Help desk staff (P3 tickets)

- Tier 2 Support: Super users (P2 tickets)

- Tier 3 Support: Vendor support (P1 tickets)

## 5.2 Issue Escalation Process

- Critical (P1): Immediate escalation, 4-hour resolution target

- High (P2): Escalate within 2 hours, 24-hour resolution target

- Medium (P3): Standard queue, 48-hour resolution target

- Low (P4): Backlog, resolved within 1 week

## 5.3 Continuous Improvement

- Weekly status review meetings

- Issue tracking and trend analysis

- User feedback sessions

- System optimization and tuning

- Training reinforcement and mini-sessions

- Regular feedback surveys and analysis

END OF DOCUMENT

Version 1.0 | June 2025